## Slide 1: Xây dựng website bán sản phẩm handmade cho cửa hàng X

## Slide 2
Chart: 
| PM | Analyst | Frontend Developer | Backend Developer | Tester | UI/UX Designer
Actual Work | 24 | 144 | 0 | 0 | 0 | 72
Remaining Work | 48 | 0 | 104 | 128 | 72 | 72

## Slide 4
Resource Overview
Chart: 
| PM | Analyst | Frontend Developer | Backend Developer | Tester | UI/UX Designer
Actual Work | 24 | 144 | 0 | 0 | 0 | 72
Remaining Work | 48 | 0 | 104 | 128 | 72 | 72
Baseline Work | 0 | 0 | 0 | 0 | 0 | 0
Resource Stats
Chart: 
| PM | Analyst | Frontend Developer | Backend Developer | Tester | UI/UX Designer
% Work Complete | 33 | 100 | 0 | 0 | 0 | 50
Work Status
Resource Status
Name | Start | Finish | Remaining Work
PM | Mon 12/23/24 | Wed 3/12/25 | 48 hrs
Analyst | Mon 12/23/24 | Tue 1/14/25 | 0 hrs
Frontend Developer | Fri 1/31/25 | Fri 2/21/25 | 104 hrs
Backend Developer | Fri 1/31/25 | Fri 2/21/25 | 128 hrs
Tester | Wed 2/19/25 | Tue 3/4/25 | 72 hrs
UI/UX Designer | Wed 1/15/25 | Thu 1/30/25 | 72 hrs

## Slide 5
Resource Cost Overview
COST STATUS
Chart: 
| PM | Analyst | Frontend Developer | Backend Developer | Tester | UI/UX Designer
Actual Cost | 14400 | 57600 | 0 | 0 | 0 | 26640
Remaining Cost | 28800 | 0 | 39520 | 53760 | 14400 | 26640
Baseline Cost | 0 | 0 | 0 | 0 | 0 | 0
COST DETAILS
Name | Actual Work | Actual Cost | Standard Rate
PM | 24 hrs | $14,400.00 | $600.00/hr
Analyst | 144 hrs | $57,600.00 | $400.00/hr
Frontend Developer | 0 hrs | $0.00 | $380.00/hr
Backend Developer | 0 hrs | $0.00 | $420.00/hr
Tester | 0 hrs | $0.00 | $200.00/hr
UI/UX Designer | 72 hrs | $26,640.00 | $370.00/hr